## Project
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | HomeLogin | Home | Guest, User | Home page before login | Việt Anh | Done | iter1 | iter2 | Complete html, css
2 | Login | Login | User | Login to quizlet | Vũ, Hùng | Done | iter2 | none
3 | Register | register | user | Register by email | Vũ, Hùng | Done | iter2 | none
4 | Log out | log out | User | Log out quizlet | Phương | Done | iter2 | none
5 | View Study set | View | Guest, User | View detail study set if they are public | Vũ | Done | iter2 | none
6 | Home | Home | User | Home page quizlet | Vũ | Done | iter2 | none
7 | View folder | View | Guest, User | View detail folder if they are public | Phương | Done | iter3 | none
8 | View class | View | Guest, User | View detail class if they are public | Việt Anh | Doing | iter3 | iter3
9 | Verify | Verifi account | User | Verify account by code send to email | Vũ | Done | iter2 | none
10 | CRUD study set | CRUD | User | Add, Edit, Delete study set | Vũ | Done | iter2 | iter3 | Complete html, css
11 | CRUD folder | CRUD | User | Add, Edit, Delete folder | Phương | Done | iter3 | iter3 | Complete feature
12 | Your library | List | User | List 5 new created study sets, folder | Hùng | Doing | iter3 | iter3 | Complete js
13 | Lời giải chuyên gia | List | Guest, User | View answer of professors | Giang | Doing | iter3 | iter3
14 | CRUD class | CRUD | User | Add, Edit, Delete class | Việt Anh | Doing | iter3 | none
15 | Search | Search | Guest, User | Search study set, folder and class by name | Giang | Doing | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Register | register | Register by email | Vũ, Hùng | Done | II.3 | II.3
2 | Logout | Log out | log out quizlet | Phương | Done | II.3 | II.3
3 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.2 | II.2
4 | Home page | Home | Home after login | Vũ | Done | II.4 | II.4
5 | Verify | Verify | Verify code from email | Vũ | Done
6 | Home Login | Home | Home before login | Việt Anh | Doing | II.5 | II.5
7 | Search | Search | Search study sets by name | Giang | Doing | II.1 | II.1
Note on G6: KienNT: The name of section in the SRS (software requirement specification) document
Note on H6: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home page | Home | Home page before Login | Việt Anh | Done | II.1 | II.1
2 | Register | register | Register by email | Vũ, Hùng | Done | II.3 | II.3
3 | Logout | Log out | log out quizlet | Phương | Done | II.3 | II.3
4 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.2 | II.2
5 | Home page | Home | Home after login | Vũ | Done | II.4 | II.4
6 | Verify | Verify | Verify code from email | Vũ | Done
7 | CRUD study sets | CRUD | View, Add, Edit, Delete study sets | Vũ | Done | II.5 | II.5
8 | Search | Search | Search study sets by name | Giang | Done | II.1 | II.1
Note on G6: KienNT: The name of section in the SRS (software requirement specification) document
Note on H6: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home page | Home | Home page before Login | Việt Anh | Done | II.1 | II.1
2 | Register | register | Register by email | Vũ, Hùng | Done | II.3 | II.3
3 | Logout | Log out | log out quizlet | Phương | Done | II.3 | II.3
4 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.2 | II.2
5 | Home page | Home | Home after login | Vũ | Done | II.4 | II.4
6 | Verify | Verify | Verify code from email | Vũ | Done
7 | CRUD folder | CRUD | View, Add, Edit, Delete folders | Phương | Done
8 | CRUD class | CRUD | View, Add, Edit, Delete class | Việt Anh | Done
9 | CRUD study sets | CRUD | View, Add, Edit, Delete study sets | Vũ | Done | II.5 | II.5
10 | Answers of professors | List | View answers of professors | Giang | Doing
11 | Library | List | List new create folders, study sets | Hùng | Doing
12 | Search | Search | Search study sets, folders and class by name | Giang | Doing | II.1 | II.1
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
2 | Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document