## Project
Total Project Tracking
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details
1 | HomeLogin | Home | Guest, User | Home page before login | Việt Anh | Done | iter1 | iter2 | Complete html, css
2 | Login | Login | User | Login to quizlet | Vũ, Hùng | Done | iter2 | none
3 | Register | register | user | Register by email | Vũ, Hùng | Done | iter2 | none
4 | Log out | log out | User | Log out quizlet | Phương | Done | iter2 | none
5 | View Study set | View | Guest, User | View detail study set if they are public | Vũ | Done | iter2 | none
6 | Home | Home | User | Home page quizlet | Vũ | Done | iter2 | none
7 | View folder | View | Guest, User | View detail folder if they are public | Phương | Done | iter3 | none
8 | View class | View | Guest, User | View detail class if they are public | Việt Anh | Done | iter3 | iter3
9 | Verify | Verifi account | User | Verify account by code send to email | Vũ | Done | iter2 | none
10 | CRUD study set | CRUD | User | Add, Edit, Delete study set | Vũ | Done | iter2 | iter3 | Complete html, css
11 | CRUD folder | CRUD | User | Add, Edit, Delete folder | Phương | Done | iter3 | iter3 | Complete feature
12 | Your library | List | User | List 5 new created study sets, folder | Hùng | Done | iter3 | iter3 | Complete js
13 | Lời giải chuyên gia | List | Guest, User | View answer of professors | Giang | Doing | iter3 | iter3
14 | CRUD class | CRUD | User | Add, Edit, Delete class | Việt Anh | Done | iter3 | iter3
15 | Study | study | User | user study their study set | Vũ | Done | iter4 | iter4
16 | List studied cards | list | User | Save studied cards | Vũ | Done | iter4 | none
17 | Reset studied cards | list | User | Reset studied card to study again study set | Vũ | Done | iter4 | none
18 | Test | Create | User | Create a test to study | Vũ | Done | iter4 | none
19 | Reset password | Update | User | Reset password when users forget password | Hùng | Done | iter4 | none
20 | Forget password | Login | User | user forget password | Hùng | Done | iter4 | none
21 | Change password | Update | User | Update new password | Phương | Done | iter4 | none
22 | Study | study | User | User can study card in study set by flash cards or multiple choice | Vũ | Done | iter4 | none
23 | Test | Test | User | Users can create a test contain 10 questions to practice and receive mark when they complete test | Vũ | Done | iter4 | none
24 | Remember cards | Select | User | List studied cards | Vũ | Done | iter4 | none
24 | Add, delete | Add, Delete study sets from folder or class | User | User can add or delete study sets from folder or class | Hùng | Done | iter4 | none
26 | Search | Search | Guest, User | Search study set, folder and class by name | Giang | Doing | iter3 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Register | register | Register by email | Vũ, Hùng | Done | II.B.2 | II.1
2 | Logout | Log out | log out quizlet | Phương | Done | II.B.7 | II.3
3 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.B.I | II.2
4 | Home page | Home | Home after login | Vũ | Done | II.C.1 | II.13
5 | Verify | Verify | Verify code from email | Vũ | Done | II.B.6 | II.5
6 | Home Login | Home | Home before login | Việt Anh | Doing | II.A.1
7 | Search | Search | Search study sets by name | Giang | Doing | II.A.2 | II.4
Note on G6: KienNT: The name of section in the SRS (software requirement specification) document
Note on H6: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home page | Home | Home page before Login | Việt Anh | Done | II.A.1
2 | Register | register | Register by email | Vũ, Hùng | Done | II.B.2 | II.1
3 | Logout | Log out | log out quizlet | Phương | Done | II.B.7 | II.3
4 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.B.I | II.2
5 | Home page | Home | Home after login | Vũ | Done | II.C.1 | II.13
6 | Verify | Verify | Verify code from email | Vũ | Done | II.B.6 | II.5
7 | CRUD study sets | CRUD | View, Add, Edit, Delete study sets | Vũ | Done | II.7.8.12 | II.3,4,5
8 | Search | Search | Search study sets by name | Giang | Done | II.A.2 | II.4
Note on G6: KienNT: The name of section in the SRS (software requirement specification) document
Note on H6: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home page | Home | Home page before Login | Việt Anh | Done | II.A.1
2 | Register | register | Register by email | Vũ, Hùng | Done | II.B.2 | II.1
3 | Logout | Log out | log out quizlet | Phương | Done | II.B.7 | II.3
4 | Login | Login | Login to quizlet | Vũ, Hùng | Done | II.B.I | II.2
5 | Home page | Home | Home after login | Vũ | Done | II.C.1 | II.13
6 | Verify | Verify | Verify code from email | Vũ | Done | II.B.6 | II.5
7 | CRUD folder | CRUD | View, Add, Edit, Delete folders | Phương | Done | II.C.6,7,8 | II.15
8 | CRUD class | CRUD | View, Add, Edit, Delete class | Việt Anh | Done | II.11,13 | II.14
9 | CRUD study sets | CRUD | View, Add, Edit, Delete study sets | Vũ | Done | II.7.8.12 | II.3,4,5
10 | Answers of professors | List | View answers of professors | Giang | Doing
11 | Library | List | List new create folders, study sets | Hùng | Doing | II.C.1 | II.13
12 | Search | Search | Search study sets, folders and class by name | Giang | Doing | II.1 | II.1
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Change password | Change password | Change password | Phương | Done | Done | Done
2 | Study | Study study set | Study cards in study sets by multiple choice | Vũ | Done | Done | Done
3 | Test | Create test | Create a test from cards in study set | Vũ | Done | Done | Done
4 | Get Studied cards | List | Cards were studied will save to list | Vũ | Done | Done | Done
5 | CRUD study set to class | CRUD | add, delete, update study sets to class | Việt Anh | Done | Done | Done
6 | CRUD folder to class | CRUD | add, delete, update folder to class | Việt Anh | Done | Done | Done
7 | CRUD member in class | CRUD | add, delete, update member to class | Việt Anh | Done | Done | Done
8 | Reset studied cards | List | Reset studied cards for user can study again | Vũ | Done | Done | Done
9 | Forget password | Forget password | When user forget password, user will use emaiil to receive link to reset email from service | Hùng | Done | Done | Done
10 | Change password | Change password | User change password | Phương | Done | Done | Done
11 | Study | Study study set | User can learn study set by flash cards or multiple choice | Vũ | Done | Done | Done
12 | Test | Test | User can create a new test,which has 10 questions and mark will present when finishing test | Vũ | Done | Done | Done
13 | CRUD Study set to class or folder | Flash Cards | In a flash card user can add or update it to folder or class | Hùng | Done | Done | Done
14 | Reset password | Reset password | User access to reset link in email to reset password, user must input new password and confrim password to reset password | Hùng | Done | Done | Done
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document